## Project Plan
S.No | Phase | Entity | Item | Sub Item | Description | Priority | Dependency | Effort (Days) | Start Date | Target Date | Owner Role | Status | Risk Level | Remarks
1 | Design | Architecture | System architecture design | Component interaction design | Define IS agent, registry, domain agent boundaries and responsibilities | P0 | - | 3 | 2026-05-04 | 2026-05-06 | Architect | Not Started | Low
2 | Design | Architecture | System architecture design | Database schema design | PostgreSQL tables for agent_cards, agent_embeddings, audit_logs, interaction_traces | P0 | S.No 1 | 2 | 2026-05-07 | 2026-05-08 | Architect | Not Started | Low
3 | Design | Architecture | System architecture design | A2A protocol mapping | Map A2A agent card schema, task lifecycle, JSON-RPC methods to internal models | P0 | S.No 1 | 2 | 2026-05-07 | 2026-05-08 | Architect | Not Started | Medium | Refer a2a-protocol.org spec
4 | Design | Architecture | System architecture design | Event-driven flow design | Redis pub/sub event schema for card_registered, card_updated, card_deregistered | P0 | S.No 1 | 1 | 2026-05-09 | 2026-05-09 | Architect | Not Started | Low
5 | Design | Architecture | System architecture design | Caching strategy design | Two-tier cache (exact + semantic), generation counter, TTL policies, eviction rules | P0 | S.No 1 | 2 | 2026-05-09 | 2026-05-10 | Architect | Not Started | Medium
6 | Design | Architecture | System architecture design | LangGraph state design | Define state schemas for discovery, slot-filling, dispatch subgraphs | P0 | S.No 1 | 2 | 2026-05-11 | 2026-05-12 | Architect | Not Started | Low
7 | Design | Security | Security architecture | Authentication design | mTLS between IS agent and domain agents, API key management for registry | P0 | S.No 1 | 2 | 2026-05-11 | 2026-05-12 | Security Lead | Not Started | High
8 | Design | Security | Security architecture | Authorization design | RBAC for agent registration, query-level access control per domain agent | P0 | S.No 7 | 2 | 2026-05-13 | 2026-05-14 | Security Lead | Not Started | High
9 | Design | Security | Security architecture | Input guardrails design | Prompt injection prevention, input sanitization, PII detection in user queries | P0 | S.No 7 | 2 | 2026-05-13 | 2026-05-14 | Security Lead | Not Started | High | Critical for enterprise
10 | Design | Security | Security architecture | Output guardrails design | Response filtering, hallucination checks, sensitive data masking in LLM outputs | P0 | S.No 9 | 1 | 2026-05-15 | 2026-05-15 | Security Lead | Not Started | High
11 | Design | Security | Security architecture | Data encryption design | Encryption at rest (PG, Redis), in transit (TLS 1.3), embedding vector protection | P1 | S.No 7 | 1 | 2026-05-15 | 2026-05-15 | Security Lead | Not Started | Medium
12 | Design | Architecture | API contract design | Registry API spec | OpenAPI spec for /register, /deregister, /health, /cards endpoints | P0 | S.No 3 | 2 | 2026-05-13 | 2026-05-14 | Architect | Not Started | Low
13 | Design | Architecture | API contract design | A2A interface spec | JSON-RPC method specs for tasks/send, tasks/get, tasks/cancel between agents | P0 | S.No 3 | 2 | 2026-05-13 | 2026-05-14 | Architect | Not Started | Medium
14 | Design | Architecture | Design review | Architecture review gate | Review all design artifacts with stakeholders, sign-off before development | P0 | S.No 1-13 | 2 | 2026-05-16 | 2026-05-17 | Architect | Not Started | Low | Gate: No dev without sign-off
15 | Infra Setup | Database | PostgreSQL setup | Database provisioning | Provision PG instance, create databases, configure connection pooling (PgBouncer) | P0 | S.No 14 | 2 | 2026-05-18 | 2026-05-19 | DevOps | Not Started | Low
16 | Infra Setup | Database | PostgreSQL setup | Schema deployment | Deploy agent_cards, agent_embeddings, audit_logs, interaction_stats tables | P0 | S.No 15 | 1 | 2026-05-20 | 2026-05-20 | DevOps | Not Started | Low
17 | Infra Setup | Database | pgvector setup | Extension and index | Install pgvector extension, create HNSW index on embedding column, tune params | P0 | S.No 16 | 1 | 2026-05-20 | 2026-05-20 | DevOps | Not Started | Medium | HNSW vs IVFFlat decision
18 | Infra Setup | Database | Redis setup | Redis provisioning | Provision Redis instance, configure pub/sub channels, set memory limits and eviction | P0 | S.No 14 | 1 | 2026-05-18 | 2026-05-18 | DevOps | Not Started | Low
19 | Infra Setup | Platform | Python environment | Runtime setup | Python 3.11+, venv, dependency management (poetry/pip), LangGraph, FastAPI | P0 | S.No 14 | 1 | 2026-05-18 | 2026-05-18 | DevOps | Not Started | Low
20 | Infra Setup | Platform | Embedding model | Model deployment | Download and deploy bge-base-en-v1.5, configure inference endpoint, benchmark latency | P0 | S.No 19 | 2 | 2026-05-19 | 2026-05-20 | ML Engineer | Not Started | Medium | Open source, runs local
21 | Infra Setup | Platform | LLM setup | LLM provisioning | Configure open-source LLM (Llama/Mistral) or API endpoint for IS agent reasoning | P0 | S.No 19 | 2 | 2026-05-19 | 2026-05-20 | ML Engineer | Not Started | High | Model selection critical
22 | Infra Setup | Security | Security infra | TLS and certificates | Generate and deploy mTLS certificates, configure TLS termination | P0 | S.No 14 | 2 | 2026-05-19 | 2026-05-20 | Security Lead | Not Started | High
23 | Infra Setup | Platform | CI/CD pipeline | Pipeline setup | Configure build, test, deploy pipeline with automated linting and security scans | P1 | S.No 19 | 2 | 2026-05-21 | 2026-05-22 | DevOps | Not Started | Low
24 | Development | Agent Registry | Registration API | POST /register endpoint | Accept A2A agent card JSON, validate schema, health-check domain agent endpoint | P0 | S.No 16 | 3 | 2026-05-23 | 2026-05-25 | Backend Dev | Not Started | Medium
25 | Development | Agent Registry | Registration API | Agent card storage | UPSERT into PostgreSQL with versioning, status tracking, timestamps | P0 | S.No 24 | 2 | 2026-05-26 | 2026-05-27 | Backend Dev | Not Started | Low
26 | Development | Agent Registry | Event publishing | Redis pub/sub integration | Publish card_registered/updated/deregistered events with full card payload | P0 | S.No 25 | 2 | 2026-05-26 | 2026-05-27 | Backend Dev | Not Started | Low
27 | Development | Agent Registry | Management API | CRUD endpoints | GET /cards, GET /cards/{id}, PUT /cards/{id}, DELETE /cards/{id}, GET /health | P1 | S.No 25 | 2 | 2026-05-28 | 2026-05-29 | Backend Dev | Not Started | Low
28 | Development | Agent Registry | Security | API authentication | API key validation middleware, rate limiting per domain agent | P0 | S.No 24 | 2 | 2026-05-28 | 2026-05-29 | Backend Dev | Not Started | High
29 | Development | IS Agent | Embedding pipeline | Event listener | Redis subscriber for card_registered events, async processing with retry logic | P0 | S.No 26 | 2 | 2026-05-28 | 2026-05-29 | Backend Dev | Not Started | Medium
30 | Development | IS Agent | Embedding pipeline | Searchable text builder | Build embedding input from card description + skill names + skill descriptions + examples | P0 | S.No 29 | 2 | 2026-05-30 | 2026-05-31 | ML Engineer | Not Started | Medium | Key for retrieval quality
31 | Development | IS Agent | Embedding pipeline | Vector generation | Integrate bge-base-en-v1.5, generate 768-dim vectors, handle batching | P0 | S.No 30 | 2 | 2026-05-30 | 2026-05-31 | ML Engineer | Not Started | Medium
32 | Development | IS Agent | Embedding pipeline | pgvector storage | UPSERT embedding with agent_id FK, manage index rebuild on bulk updates | P0 | S.No 31 | 1 | 2026-06-01 | 2026-06-01 | Backend Dev | Not Started | Low
33 | Development | IS Agent | Embedding pipeline | Cache invalidation | INCR routing_cache_generation on each new embedding, handle startup re-index | P0 | S.No 32 | 1 | 2026-06-01 | 2026-06-01 | Backend Dev | Not Started | Low
34 | Development | IS Agent | Discovery engine | Query normalization | Lowercase, whitespace stripping, punctuation removal, SHA-256 hashing | P0 | S.No 19 | 1 | 2026-06-02 | 2026-06-02 | Backend Dev | Not Started | Low
35 | Development | IS Agent | Discovery engine | Tier 1: Exact cache | Redis HGETALL with generation counter validation, TTL management | P0 | S.No 34 | 2 | 2026-06-02 | 2026-06-03 | Backend Dev | Not Started | Low
36 | Development | IS Agent | Discovery engine | Query embedding | Generate query embedding using same bge-base-en-v1.5 model instance | P0 | S.No 31 | 1 | 2026-06-04 | 2026-06-04 | ML Engineer | Not Started | Low | Must share model with I3
37 | Development | IS Agent | Discovery engine | Tier 2: Semantic cache | Cosine similarity comparison against cached query embeddings (threshold 0.95) | P0 | S.No 36 | 2 | 2026-06-04 | 2026-06-05 | Backend Dev | Not Started | Medium
38 | Development | IS Agent | Discovery engine | pgvector search | Top-5 similarity search with threshold filter (>0.65), fetch full cards from PG | P0 | S.No 37 | 2 | 2026-06-06 | 2026-06-07 | Backend Dev | Not Started | Medium
39 | Development | IS Agent | Discovery engine | LLM-assisted selection | Prompt template for multi-candidate reasoning, single-candidate bypass logic | P0 | S.No 38 | 3 | 2026-06-06 | 2026-06-08 | ML Engineer | Not Started | High | Prompt engineering critical
40 | Development | IS Agent | Discovery engine | Cache write-back | Store routing decision in both exact and semantic cache tiers with generation# | P0 | S.No 39 | 1 | 2026-06-09 | 2026-06-09 | Backend Dev | Not Started | Low
41 | Development | IS Agent | Slot-filling engine | LangGraph state machine | Define SlotFillingState, build graph: extract → check → ask/confirm → dispatch | P0 | S.No 6 | 3 | 2026-06-09 | 2026-06-11 | Backend Dev | Not Started | High | Core orchestration logic
42 | Development | IS Agent | Slot-filling engine | LLM slot extraction | Extract structured values from NL: date resolution, enum mapping, validation | P0 | S.No 41 | 3 | 2026-06-12 | 2026-06-14 | ML Engineer | Not Started | High | Prompt engineering critical
43 | Development | IS Agent | Slot-filling engine | Session management | Redis session create/read/update/delete, TTL 30min, abandoned session cleanup | P0 | S.No 41 | 2 | 2026-06-12 | 2026-06-13 | Backend Dev | Not Started | Low
44 | Development | IS Agent | Slot-filling engine | Conversational question gen | LLM generates natural questions for missing slots, batches related fields | P0 | S.No 42 | 2 | 2026-06-15 | 2026-06-16 | ML Engineer | Not Started | Medium
45 | Development | IS Agent | Slot-filling engine | Confirmation flow | Build human-readable summary, handle yes/no/edit responses | P0 | S.No 44 | 2 | 2026-06-15 | 2026-06-16 | Backend Dev | Not Started | Low
46 | Development | IS Agent | Slot-filling engine | Intent switch detection | Detect when user changes topic mid-conversation, park/resume sessions | P1 | S.No 41 | 2 | 2026-06-17 | 2026-06-18 | ML Engineer | Not Started | Medium
47 | Development | IS Agent | Slot-filling engine | Correction handling | Detect and overwrite previously filled slots when user corrects values | P1 | S.No 42 | 1 | 2026-06-17 | 2026-06-17 | Backend Dev | Not Started | Medium
48 | Development | IS Agent | A2A dispatch | Task payload builder | Build JSON-RPC tasks/send payload from filled slots + target agent endpoint | P0 | S.No 13 | 2 | 2026-06-17 | 2026-06-18 | Backend Dev | Not Started | Medium
49 | Development | IS Agent | A2A dispatch | HTTP client | Async HTTP client with mTLS, retry with backoff, timeout handling, circuit breaker | P0 | S.No 48 | 2 | 2026-06-19 | 2026-06-20 | Backend Dev | Not Started | Medium
50 | Development | IS Agent | A2A dispatch | Response handler | Parse task response, handle success/error/working states, validation error re-routing | P0 | S.No 49 | 2 | 2026-06-19 | 2026-06-20 | Backend Dev | Not Started | Medium
51 | Development | IS Agent | A2A dispatch | Response formatter | LLM formats domain agent response into natural language for user | P0 | S.No 50 | 2 | 2026-06-21 | 2026-06-22 | ML Engineer | Not Started | Low
52 | Development | IS Agent | Guardrails | Input sanitization | Validate and sanitize user input, prevent prompt injection attacks | P0 | S.No 9 | 3 | 2026-06-21 | 2026-06-23 | Security Dev | Not Started | High | Enterprise security req
53 | Development | IS Agent | Guardrails | PII detection | Detect and mask PII in user queries before logging or passing to LLM | P0 | S.No 52 | 2 | 2026-06-24 | 2026-06-25 | Security Dev | Not Started | High
54 | Development | IS Agent | Guardrails | Output filtering | Validate LLM outputs, filter hallucinations, mask sensitive data in responses | P0 | S.No 10 | 2 | 2026-06-24 | 2026-06-25 | Security Dev | Not Started | High
55 | Development | IS Agent | Guardrails | Rate limiting | Per-user and per-agent rate limiting with Redis token bucket | P1 | S.No 35 | 1 | 2026-06-26 | 2026-06-26 | Backend Dev | Not Started | Medium
56 | Development | IS Agent | Guardrails | Audit logging | Log full interaction trace to PostgreSQL: query → route → slots → dispatch → result | P0 | S.No 25 | 2 | 2026-06-26 | 2026-06-27 | Backend Dev | Not Started | Low
57 | Development | Domain Agent | Sample HR agent | A2A server implementation | FastAPI A2A-compliant server with tasks/send, tasks/get endpoints | P0 | S.No 13 | 3 | 2026-05-30 | 2026-06-01 | Backend Dev | Not Started | Medium | For E2E testing
58 | Development | Domain Agent | Sample HR agent | Agent card definition | Define agent card with leave, payroll skills, input schemas, example queries | P0 | S.No 57 | 1 | 2026-06-02 | 2026-06-02 | Backend Dev | Not Started | Low
59 | Development | Domain Agent | Sample HR agent | Business logic stub | Mock leave application, balance check, payroll query with realistic responses | P0 | S.No 57 | 2 | 2026-06-02 | 2026-06-03 | Backend Dev | Not Started | Low
60 | Development | Domain Agent | Sample IT agent | Second domain agent | IT helpdesk agent with ticket creation, status check, password reset skills | P1 | S.No 57 | 3 | 2026-06-04 | 2026-06-06 | Backend Dev | Not Started | Low | For multi-agent testing
61 | Testing | Agent Registry | Unit tests | Registry unit tests | Schema validation, CRUD operations, event publishing, error handling | P0 | S.No 28 | 3 | 2026-06-28 | 2026-06-30 | QA Engineer | Not Started | Low
62 | Testing | IS Agent | Unit tests | Discovery engine unit tests | Cache hit/miss paths, vector search, LLM selection mock, normalization | P0 | S.No 40 | 3 | 2026-06-28 | 2026-06-30 | QA Engineer | Not Started | Medium
63 | Testing | IS Agent | Unit tests | Slot-filling unit tests | Slot extraction accuracy, completeness check, correction handling, session lifecycle | P0 | S.No 47 | 3 | 2026-06-28 | 2026-06-30 | QA Engineer | Not Started | Medium
64 | Testing | IS Agent | Unit tests | A2A dispatch unit tests | Payload construction, error handling, retry logic, response parsing | P0 | S.No 51 | 2 | 2026-07-01 | 2026-07-02 | QA Engineer | Not Started | Low
65 | Testing | All | Integration tests | Registration E2E | Domain agent registers → PG stored → event published → IS agent embeds → pgvector stored | P0 | S.No 60 | 3 | 2026-07-01 | 2026-07-03 | QA Engineer | Not Started | High
66 | Testing | All | Integration tests | Discovery E2E | User query → cache miss → pgvector search → LLM select → cache write → verify routing | P0 | S.No 65 | 3 | 2026-07-04 | 2026-07-06 | QA Engineer | Not Started | High
67 | Testing | All | Integration tests | Slot filling E2E | Multi-turn conversation → slot extraction → confirmation → A2A dispatch → response | P0 | S.No 66 | 3 | 2026-07-04 | 2026-07-06 | QA Engineer | Not Started | High
68 | Testing | All | Integration tests | Cache invalidation E2E | New agent registers → cache generation increments → next query bypasses stale cache | P0 | S.No 66 | 2 | 2026-07-07 | 2026-07-08 | QA Engineer | Not Started | Medium
69 | Testing | Security | Security testing | Prompt injection tests | Test injection via user queries, agent card descriptions, skill examples | P0 | S.No 54 | 3 | 2026-07-07 | 2026-07-09 | Security QA | Not Started | High | Must pass before go-live
70 | Testing | Security | Security testing | Authentication tests | mTLS validation, API key rotation, expired cert handling, unauthorized access | P0 | S.No 22 | 2 | 2026-07-07 | 2026-07-08 | Security QA | Not Started | High
71 | Testing | Security | Security testing | PII leakage tests | Verify PII masking in logs, LLM prompts, cached data, audit trail | P0 | S.No 53 | 2 | 2026-07-10 | 2026-07-11 | Security QA | Not Started | High
72 | Testing | IS Agent | Performance tests | Discovery latency | Measure P50/P95/P99 latency for cache hit, cache miss, and full discovery paths | P1 | S.No 66 | 2 | 2026-07-10 | 2026-07-11 | QA Engineer | Not Started | Medium | Target: <500ms P95 cache miss
73 | Testing | IS Agent | Performance tests | Embedding throughput | Benchmark embedding generation speed, pgvector query latency under load | P1 | S.No 72 | 2 | 2026-07-12 | 2026-07-13 | QA Engineer | Not Started | Medium
74 | Testing | IS Agent | Performance tests | Cache hit rate analysis | Simulate realistic query distribution, measure Tier1 vs Tier2 vs miss ratios | P1 | S.No 73 | 1 | 2026-07-12 | 2026-07-12 | QA Engineer | Not Started | Low | Target: >70% hit rate
75 | Testing | IS Agent | Quality tests | Retrieval accuracy eval | Evaluate agent routing accuracy across 100+ test queries, measure precision/recall | P0 | S.No 66 | 3 | 2026-07-10 | 2026-07-12 | ML Engineer | Not Started | High | Must achieve >90% accuracy
76 | Testing | IS Agent | Quality tests | Slot extraction accuracy | Evaluate slot extraction across date formats, enum values, multi-field messages | P0 | S.No 67 | 2 | 2026-07-13 | 2026-07-14 | ML Engineer | Not Started | High
77 | Testing | All | UAT | User acceptance testing | End-to-end testing with real users, multiple domain agents, realistic scenarios | P0 | S.No 76 | 5 | 2026-07-15 | 2026-07-19 | Product Owner | Not Started | Medium
78 | Testing | All | UAT | UAT defect resolution | Fix issues identified during UAT, re-test, sign-off | P0 | S.No 77 | 3 | 2026-07-20 | 2026-07-22 | Backend Dev | Not Started | Medium
79 | Deployment | All | Deployment prep | Deployment runbook | Step-by-step deployment guide, rollback procedures, health check scripts | P0 | S.No 78 | 2 | 2026-07-23 | 2026-07-24 | DevOps | Not Started | Low
80 | Deployment | All | Deployment prep | Configuration management | Environment-specific configs, secrets management (Vault/k8s secrets), feature flags | P0 | S.No 79 | 2 | 2026-07-23 | 2026-07-24 | DevOps | Not Started | Medium
81 | Deployment | All | Staging deployment | Deploy to staging | Full deployment to staging environment, smoke tests, integration verification | P0 | S.No 80 | 2 | 2026-07-25 | 2026-07-26 | DevOps | Not Started | Medium
82 | Deployment | All | Staging deployment | Staging validation | Run full test suite on staging, performance baseline, security scan | P0 | S.No 81 | 2 | 2026-07-27 | 2026-07-28 | QA Engineer | Not Started | Medium
83 | Deployment | All | Production deployment | Production deploy | Rolling deployment to production, canary release, traffic shifting | P0 | S.No 82 | 1 | 2026-07-29 | 2026-07-29 | DevOps | Not Started | High | Change window required
84 | Deployment | All | Production deployment | Post-deploy validation | Health checks, smoke tests, verify agent registration, test discovery flow | P0 | S.No 83 | 1 | 2026-07-30 | 2026-07-30 | DevOps | Not Started | High
85 | Deployment | All | Production deployment | Go-live sign-off | Stakeholder sign-off, confirm monitoring active, close deployment ticket | P0 | S.No 84 | 1 | 2026-07-30 | 2026-07-30 | Product Owner | Not Started | Low | Gate: Formal sign-off
86 | Monitoring | All | Observability setup | Metrics collection | Prometheus metrics: discovery latency, cache hit rate, LLM call duration, error rates | P0 | S.No 81 | 3 | 2026-07-25 | 2026-07-27 | DevOps | Not Started | Medium
87 | Monitoring | All | Observability setup | Dashboard creation | Grafana dashboards: system health, agent routing, cache performance, error trends | P0 | S.No 86 | 2 | 2026-07-28 | 2026-07-29 | DevOps | Not Started | Low
88 | Monitoring | All | Observability setup | Distributed tracing | OpenTelemetry traces across IS agent → registry → domain agent → databases | P1 | S.No 86 | 2 | 2026-07-28 | 2026-07-29 | DevOps | Not Started | Medium
89 | Monitoring | All | Observability setup | Log aggregation | Centralized logging (ELK/Loki), structured JSON logs, correlation IDs | P0 | S.No 86 | 2 | 2026-07-28 | 2026-07-29 | DevOps | Not Started | Low
90 | Monitoring | All | Alerting | Alert rules | PagerDuty/Slack alerts: discovery failures, cache miss spike, LLM errors, agent down | P0 | S.No 87 | 2 | 2026-07-30 | 2026-07-31 | DevOps | Not Started | Medium
91 | Monitoring | IS Agent | Continuous quality | Routing accuracy tracking | Weekly eval of routing decisions against ground truth, drift detection | P0 | S.No 75 | 2 | 2026-07-30 | 2026-07-31 | ML Engineer | Not Started | High | Ongoing post go-live
92 | Monitoring | IS Agent | Continuous quality | Embedding model monitoring | Track embedding quality degradation, trigger re-indexing when new agents added | P1 | S.No 91 | 2 | 2026-08-01 | 2026-08-02 | ML Engineer | Not Started | Medium
93 | Monitoring | All | Runbook | Operations runbook | Troubleshooting guides: cache flush, manual re-embed, agent deregistration, rollback | P0 | S.No 87 | 2 | 2026-08-01 | 2026-08-02 | DevOps | Not Started | Low
94 | Monitoring | All | Runbook | Incident response plan | Escalation paths, severity definitions, communication templates, post-mortem process | P0 | S.No 93 | 1 | 2026-08-03 | 2026-08-03 | DevOps | Not Started | Low

## Summary
Multi-Agent Orchestration — Project Summary
Phase | Total Items | P0 Items | P1 Items | Total Effort (Days) | Duration (Calendar Days)
Design | 14 | 13 | 1 | 26 | 14 days
Infra Setup | 9 | 8 | 1 | 14 | 5 days
Development | 37 | 32 | 5 | 73 | 36 days
Testing | 18 | 15 | 3 | 47 | 25 days
Deployment | 7 | 7 | 0 | 11 | 8 days
Monitoring | 9 | 7 | 2 | 18 | 10 days
TOTAL | 94 | 82 | 12 | 189 | 92 days (~13 weeks)
Key Assumptions & Notes
1. Start date: 04-May-2026 (Monday). Calendar days include weekends; effort days are working days only.
2. Team composition: 1 Architect, 2 Backend Devs, 1 ML Engineer, 1 Security Lead/Dev, 1 DevOps, 1 QA, 1 Product Owner.
3. Some tasks run in parallel (e.g., domain agent dev overlaps with IS agent dev). See dependency column for sequencing.
4. P0 = Must have for launch. P1 = Important but can follow in next sprint if needed.
5. Security items (guardrails, PII, prompt injection) are non-negotiable P0 for enterprise deployment.
6. LLM model selection (S.No 21) is the highest-risk item — affects all downstream prompt engineering.
7. Retrieval accuracy eval (S.No 75) must achieve >90% before UAT. This is the quality gate.
8. Monitoring setup (S.No 86-94) starts during staging to ensure observability is ready at go-live.